## PI_IT_Outsourced
Task Assigned To | Target Date | Completed | Hours | % | Status | Action Item | Comments
Kick Off Phase
Donna | 2007-09-01 | 2007-10-11 | 4 | 6.084% | complete | RFP to Telus, CDMS
Donna | 2007-10-24 | 2007-10-24 | 3 | 4.563% | complete | Meeting with CMDS onsite facilites visit
Donna /Claude | 2007-11-09 | 2007-11-09 | 5 | 7.605% | complete | Meeting with CMDS onsite facilites / Proposal overview
MAB/ Donna / Claude / CDMS | 2007-12-11 | 2007-12-11 | 3 | 4.563% | complete | Meeting with CDMS Network Specialists review SOW
CMDS Yves | 2007-12-12 | 2007-12-12 |  |  | complete | Site Survey
Donna / Claude | 2007-12-11 | 2007-12-11 | 0.25 | 0.3802% | complete | Positron.ca Internal Domain
CMDS / MAB | 2007-12-11 | 2007-12-18 | 0.25 | 0.3802% | complete | Prepare Survey for Policies of New Netowrk / Exchange limitations / AD policies
CMDS | 2007-12-11 | 2007-12-11 |  |  | complete | Confirm Firewall specs
SUB TOTAL |  |  | 15.5 | 23.57%
Initial Ordering and Preparation Phase
Donna | 2007-11-09 | 2007-11-09 | 2.5 | 3.802% | complete | Review Equipment proposal
Donna | 2007-11-09 | 2007-11-09 | 1.5 | 2.281% | complete | Validate CDMS pricing with PI corporate pricing
Donna | 2007-11-09 | 2007-11-09 | 1 | 1.521% | complete | Order Firewall with Insight
Tarek | 2007-11-15 | 2007-11-15 | 0.25 | 0.3802% | complete | Enter order in SM
Donna | 2007-12-07 | 2007-12-07 | 1.5 | 2.281% | complete | RFP for Internet upgrade
Donna | 2007-12-14 | 2007-12-14 | 1.5 | 2.281% | complete | Order Internet upgrade
Marc Alexandres Belanger | 2007-12-03 | 2007-12-03 | 2 | 3.042% | complete | ExMerge MS Exchange Power/PI accounts backup
Donna | 2008-01-31 |  | 0.25 | 0.3802% | In Progress | Contact Finance about any Software (central) | Waiting for response
Louis Rene Beaudoin/Patrick Robineau | 2008-01-31 |  | 0.25 | 0.3802% | In Progress | Contact Patrick Robineau for Lic. Key info so switch prod | Waiting for response
Donna /Claude | 2008-01-31 |  | 2 | 3.042% | In Progress | Anti Spam / Anti Virus Total Protection for McAfee | Quotes received for McAfee sent to Claude will meet on Jan 18th
0%
0%
0%
SUB TOTAL |  |  | 12.75 | 19.39%
Phase III Equipment Deployement / Network preparation
Tarek | 2007-12-03 | 2007-12-03 | 1.5 | 2.281% | complete | Receive and inventory in SM
Marc Alexandre / Harold | 2008-01-16 |  | 12 | 18.25% | In Progress | Confirgure ASA 5510 Firewall | Harold to contact Marc before Wednesday
CDMS | 2007-01-16 | 2007-01-17 |  |  | complete | We will be on site Wednesday morning to collect some final information for our migration we will be there for about 10:00AM. ( 1.5 hours max )
CDMS | 2007-01-17 |  |  |  |  | We will be there Thursday morning to install the equipment 10:00AM ( 1.5 hours max )
Donna / Claude | 2007-01-18 |  | 2 |  |  | Review weekend Go Live CDMS IT Outsourcing task list
SUB TOTAL |  |  | 15.5 | 23.57%
Cut Over
CDMS | 2007-01-18 |  |  | 0% |  | We will be there Friday afternoon for 4:00PM migration will start 5:00PM
Marc Alexandres Belanger / IS Staff TBA | 2007-01-18 |  | 2 | 0% |  | Test all ManMan functions / ODBC / FTP / NSVT / Printing / Transactions / Label printing / etc.
Marc Alexandres Belanger | 2007-01-18 |  | 1 | 1.521% |  | Test www.positronpower.com / Call Manager Express remote management
Marc Alexandre / Patrick Robineau/CDMS | 2008-01-18 |  | 3 | 4.563% |  | Migrate switchProd data from Srvagile05 to new File server
CDMS/ Marc Alex | 2008-01-18 |  | 3 | 4.563% |  | Migrate Printers from Srvagile05
CDMS/ Marc Alex | 2008-01-18 |  | 3 | 4.563% |  | Migrate Shares
Marc Alexandres Belanger | 2008-01-18 |  | 1 | 1.521% |  | ExMerge MS Exchange Power/PI accounts backup / to move to new server
Marc Alexandres Belanger | 2008-01-18 |  | 1 | 1.521% |  | Create Secure ftp site for month end reports pickup
Ovid | 2008-01-18 |  | 1 |  |  | FTP process for Month End reports pickup
Ovid | 2008-01-18 |  | 0.5 |  |  | ManMan backup media transfer logistics from TRITON to PI
SUB TOTAL |  |  | 15.5 | 23.57%
Phase V Post Cut
CDMS | 1/212008 |  |  |  |  | CDMS Technician onsite for hands on troubleshooting
CMDS | 2008-01-18 |  |  |  |  | Work out local Firewall protection for Laptops / AD Policies
CMDS / Claude | 2008-01-18 |  |  |  |  | Web Filtering Solution required? Purchase necc.
CMDS / Claude | 2008-01-18 |  |  |  |  | Lock Down? Policies and Procedures
CDMS | 2008-01-31 |  |  |  |  | helpDesk logistics training and implementation
CDMS / Claude | 2008-01-31 |  |  |  |  | Backup logisitics knowledge transfer
CDMS | 2008-01-31 |  |  |  |  | Communication to all PI employees of new IT Support Company/proedures
Donna / Claude | 2008-01-31 |  | 1 | 1.521% |  | Domain name registration transfers
Donna / Claude | 2008-01-31 |  | 2 | 3.042% |  | Recall Offsite management knowledge transfer
Donna / Claude | 2008-01-31 | 2008-01-18 | 2 | 3.042% | complete | Vendor contact transfer | \\Srvagile05\it\itkb\IT_Contacts
CDMS / Marc Alex | 2008-01-31 |  | 1.5 | 2.281% |  | Change Speed dial on all phones to CDMS helpe desk number
CDMS / PI | 2008-01-31 |  |  |  |  | Knowledge Transfer misc
SUB TOTAL |  |  | 6.5 | 9.886%
GRAND TOTAL |  |  | 65.75 | 100%
% Project complete |  |  | 0 | 41.44%

## Key Personnel
DATE:
TASK LIST
SPECIAL NOTES:
KEY PERSONNEL
COMPANY | NAME | TITLE | PHONE | CELL or PAGER | email | COMMENTS
Positron | Donna Koussaya | IT Networking Manager | 514-782-3111 Ext 4586 | 514-916-3687 | dkoussaya@positron.qc.ca
Positron | Marc Alexandre Belanger | Network Administrator | 514-782-3111 Ext. 4869 | 514-715-7813 | mabelanger@positron-tech.com
Positron | Claude Brisson | COO Positron | 514-345-2241 | 514-916-1410
CDMS | Silvio Dipilato | Project Manager | 514-286-2367 | 514-774-7535 | sdipilato@cdmsfirst.com
CDMS | Yves Melancon | Specialiste en post de travail | 514-286-2367 Ext. 282 | 514-267-2967
CDMS | Chris Symeon | President | 514-286-8053 | 514-891-2970 | csymeon@cdmsfirst.com